## Sheet1
Task | Status | End Date
Get List category | Done
Get List tag | Done
Oauth2 - With user name and pass in code | Done
Oauth2 - With user name and pass in Database | making | 15/3/2020
Upload Image | waiting | 22/3/2020
Paging | Waiting | 25/3/2020
CRUD User | Waiting | 28/3/2020
CRUD Category | Waiting | 2020-01-04
CRUD Tag color | Waiting | 2020-04-04
Search Image | Waiting | 2020-08-04
Category Path | Waiting | 2020-09-04
Download Image by Zip | Waiting
Make exel user infor | Waiting
Download Image | Waiting
Delete Image | Waiting
Setup into Server | Waiting